## 02-stories
# | Issue key | Issue id | Custom field (Epic Link) | Ename | Assignee | Custom field (Story Points) | teste | Original Estimate | Time Spent | Remaining Estimate | Sprint | Sprint2 | Sprint3 | Summary
1 | PCS-28233 | 596065 | PCS-28016 | May21-21xPCS | ssubramanian | 4 |  | 57600 | 57600 | 0 | PCS-2124 |  |  | [ISA8K]: System is allowing more than permitted Licenses
2 | PCS-28264 | 596185 | PCS-28016 | May21-21xPCS | ssubramanian | 4 |  | 57600 | 57600 | 0 | PCS-2124 |  |  | [ISA8K-F]:Able to establish 25K Tunnels without licenses
3 | PCS-28333 | 596498 | PCS-28322 | May21-New Platform support | ssubramanian | 6 |  | 86400 | 86400 | 0 | PCS-2124 |  |  | ISA8K Platform porting document-part1
4 | PCS-27371 | 592012 | PCS-28322 | May21-New Platform support | ssubramanian | 4 |  | 57600 | 57600 | 0 | PCS-2124 |  |  | SM HW: Licensing Dev Information Documentation
5 | PCS-27022 | 590514 | PCS-28017 | May21-Deployment-Phase2 | rajeshg | 6 |  | 86400 | 64800 | 21600 | PCS-2118 | PCS-2120 | PCS-2124 | SuperDoctor: Confirm SuperDoctor diagnostic tool with SM-HW port
6 | PCS-28232 | 596064 | PCS-28017 | May21-Deployment-Phase2 | rajeshg | 4 |  | 57600 | 115200 | 0 | PCS-2124 |  |  | [ISA8K]: HW status & other information missing from Admin UI
7 | PCS-28332 | 596496 | PCS-28017 | May21-Deployment-Phase2 | rajeshg | 6 |  | 86400 | 10800 | 75600 | PCS-2124 | PCS-2126 |  | SM-HW: Pixe Packaging - Testing on HW
8 | PCS-28312 | 596429 | PCS-28311 | May21-Baseline | praveens | 4 |  | 57600 | 115200 | 0 | PCS-2124 |  |  | QA-ISA8K-Perf Baseline: Max Users/Tunnel Setup count(ESP)
9 | PCS-28318 | 596435 | PCS-28311 | May21-Baseline | praveens | 4 |  | 57600 | 57600 | 0 | PCS-2124 |  |  | QA-ISA8K-Perf Baseline: Tunnel setup rate tests(ESP)
10 | PCS-28319 | 596436 | PCS-28311 | May21-Baseline | praveens | 6 |  | 86400 | 86400 | 0 | PCS-2124 |  |  | QA-ISA8K-Perf Baseline: Baseline the Max Throughput(ESP)
11 | PCS-28441 | 596948 | PCS-28322 | May21-New Platform support | praveens | 2 |  | 28800 | 50400 | 0 | PCS-2124 |  |  | [SM-HW]: Investigate the issue where admin UI is not accessible on HW 38
12 | PCS-28313 | 596430 | PCS-28311 | May21-Baseline | karthikr | 4 |  | 7200 | 115200 | 0 | PCS-2124 |  |  | QA-ISA8K-Perf Baseline: Max Users/Tunnel Setup count(SSL)
13 | PCS-28315 | 596432 | PCS-28311 | May21-Baseline | karthikr | 6 |  | 86400 | 28800 | 0 | PCS-2124 | PCS-2126 |  | QA-ISA8K-Perf Baseline: Baseline the Max Throughput(SSL)
14 | PCS-26807 | 589433 | PCS-28017 | May21-Deployment-Phase2 | kalaimani.k | 8 |  | 115200 | 28800 | 0 | PCS-2114 | PCS-2124 |  | SMHW: Checking BIOS configuration
15 | PCS-28334 | 596499 | PCS-28322 | May21-New Platform support | kalaimani.k | 6 |  | 86400 | 172800 | 0 | PCS-2124 |  |  | ISA8K Platform porting document (Driver related)
16 | PCS-28663 | 597761 | PCS-28322 | May21-New Platform support | kalaimani.k | 4 |  | 1200 | 57600 | 0 | PCS-2124 |  |  | SM-HW: Analysis and Explore the Secure Boot option on SM HW
17 | PCS-28355 | 596647 | PCS-28016 | May21-21xPCS | balajit | 6 |  | 86400 | 104400 | 0 | PCS-2124 |  |  | SM-HW: ISA8000 License parameters information collection
18 | PCS-28357 | 596652 | PCS-28016 | May21-21xPCS | balajit | 6 |  | 86400 | 57600 | 28800 | PCS-2124 |  |  | SM HW: CPU Affinity Usage Checking during traffic
19 | PCS-28390 | 596746 | PCS-28016 | May21-21xPCS | balajit | 4 |  | 57600 | 57600 | 0 | PCS-2124 |  |  | SM-HW: ISA8000 License checking support
20 | PCS-28314 | 596431 | PCS-28311 | May21-Baseline | balachandras | 6 |  | 86400 | 57600 | 0 | PCS-2124 | PCS-2126 |  | QA-ISA8K-Perf Baseline: Tunnel setup rate tests(SSL)
21 | PCS-28316 | 596433 | PCS-28311 | May21-Baseline | balachandras | 8 |  | 14400 | 144000 | 0 | PCS-2124 | PCS-2126 |  | QA-ISA8K-Perf Baseline: Throughput-Standard/less packet sizes/varied user load(SSL)
22 | PCS-28438 | 596940 | PCS-28322 | May21-New Platform support | balachandras | 2 |  | 28800 | 57600 | 0 | PCS-2124 |  |  | [SM HW]: Flashing serial number to BIOS

## 01-epics
# | Custom field (Epic Link) | Ename | ESdate | ETdate | EASDate | EAEDate
1 | PCS-28018 | May21-Performance | 2021-05-20 | 2021-06-17 | 2021-05-20 | 2021-06-17
2 | PCS-28042 | May21-ISA8000x-Support | 2021-05-20 | 2021-06-03 | 2021-05-20 | 2021-06-03
3 | PCS-28017 | May21-Deployment-Phase2 | 2021-05-20 | 2021-06-03 | 2021-05-20 | 2021-06-03
4 | PCS-28016 | May21-21xPCS | 2021-05-20 | 2021-06-17 | 2021-05-20 | 2021-06-17
5 | PCS-28322 | May21-New Platform support | 2021-05-20 | 2021-06-17 | 2021-05-20 | 2021-06-17
6 | PCS-28311 | May21-Baseline | 2021-05-04 | 2021-07-13 | 2021-05-04 | 2021-06-17